GEAROPS

DEPLOYMENT STRATEGY

Project Manager Guide

Web  •  iOS  •  Android

Go Codes → GearOps Migration

Prepared: April 2026

gearops.com.au

# 1. Executive Summary

GearOps is the organisation’s next-generation asset management platform, replacing the legacy Go Codes system. This document is the master deployment guide for the Project Manager responsible for coordinating the rollout across three platforms — web, iOS, and Android — alongside the physical migration of 100–500 assets.

The rollout is structured across five phases, from internal testing through to full live deployment and stabilisation. The physical migration component (sticker removal, new sticker placement, new gear allocation) runs in parallel with the technical deployment work.

# 2. Scope of This Deployment

## 2.1 Platforms

- Web — gearops.com.au (already live; this deployment completes full feature parity and stability)

- iOS — Currently on TestFlight; target is App Store public release

- Android — New platform; target is Google Play Store release

## 2.2 Migration Scope

- Migrate 100–500 assets from Go Codes to GearOps

- Remove old Go Codes stickers from all migrated assets

- Apply new GearOps QR/barcode stickers to all migrated assets

- Allocate any newly acquired gear directly in GearOps (not Go Codes)

- Decommission Go Codes once migration and validation are complete

## 2.3 Out of Scope

- Modification of existing backend API contracts (no breaking changes)

- New feature development during the rollout window

- Client-facing portals or third-party integrations in this phase

# 3. Deployment Phases

The deployment is organised into five sequential phases. Each phase has a defined gate — do not proceed to the next phase until all gate criteria are met.

| Phase | Name | Activities | Duration | Status |
| --- | --- | --- | --- | --- |
| Phase 1 | Testing & Hardening | Internal QA on TestFlight (iOS) + web staging. Bug triage, UI polish, performance validation. | 2 weeks | PLANNED |
| Phase 2 | Pilot Migration | Select 50 assets migrated from Go Codes to GearOps. New stickers printed + applied. Staff trained. | 1 week | PLANNED |
| Phase 3 | Full Asset Migration | Remaining 100–500 assets migrated. Old stickers removed, GearOps stickers placed. New gear allocated directly in GearOps. | 3 weeks | PLANNED |
| Phase 4 | Go Live – All Platforms | Web (gearops.com.au) + iOS App Store + Android Play Store fully live. Go Codes decommissioned. | 1 week | PLANNED |
| Phase 5 | Stabilisation | Monitor, user support, hotfixes, performance review. | Ongoing | PLANNED |

## Phase Gates

### Phase 1 → Phase 2: Testing Complete

- Zero P0/P1 (critical/major) bugs outstanding

- All core flows pass on iOS, Android and Web

- Staging environment stable for 48+ hours

### Phase 2 → Phase 3: Pilot Signed Off

- All 50 pilot assets scanned and verified in GearOps

- Field tech confirms sticker scan accuracy 100%

- Project Lead sign-off documented

### Phase 3 → Phase 4: Migration Complete

- All 100–500 assets migrated, stickered, and verified

- New gear allocation process confirmed working

- No outstanding data discrepancies

### Phase 4 → Phase 5: Go Live

- iOS app published on App Store

- Android app published on Google Play

- Go Codes formally decommissioned

- Staff notified via email/meeting

# 4. Roles & Responsibilities (RACI)

R = Responsible  •  A = Accountable  •  C = Consulted  •  I = Informed

| Activity | Project Lead | Field Tech | Dev / IT | Office Mgr |
| --- | --- | --- | --- | --- |
| Migrate asset records from Go Codes | R/A | C | I | I |
| Remove old Go Codes stickers | A | R | I | - |
| Apply new GearOps stickers | A | R | I | - |
| Allocate new gear in GearOps | R/A | C | I | I |
| iOS TestFlight build & submit | I | I | R/A | C |
| Android build & Play Store submit | I | I | R/A | C |
| Web deployment (gearops.com.au) | I | I | R/A | C |
| User training – field technicians | A | I | I | R |
| User training – office staff | A | R | I | I |
| Supabase schema migrations | I | I | R/A | C |
| Go Codes decommission sign-off | R/A | C | C | I |

# 5. Testing Plan

## 5.1 Testing Approach

All testing must be completed before Phase 2 begins. Testing covers three tracks:

- Functional Testing — Core user workflows on all platforms

- Performed by Dev/IT team on real devices

- iOS: iPhone 14+ via TestFlight. Android: physical device + emulator

- Web: Chrome, Safari, Firefox (desktop + mobile)

- Field Testing — Real-world QR scan and asset workflows

- Performed by field technicians with actual asset stickers

- Validate speed of scan-to-record in various lighting conditions

- Data Testing — Migration integrity and import validation

- Performed by Dev/IT

- Row count reconciliation, field-level spot checks, duplicate detection

## 5.2 Test Checklist

Log all results in the table below. All items must be PASS before Phase 2 gate.

|  | Test Case | Tester | Result (Pass / Fail / Note) |
| --- | --- | --- | --- |
| Web | Login / logout flow on gearops.com.au | Dev / IT |  |
| Web | Asset search, filter, and pagination | Dev / IT |  |
| Web | Asset create, edit, delete | Dev / IT |  |
| Web | Dashboard stats load correctly | Dev / IT |  |
| Web | Responsive layout (mobile browser) | Dev / IT |  |
| iOS | TestFlight install on iPhone | Dev / IT |  |
| iOS | QR scan opens correct asset | Field Tech |  |
| iOS | Asset status update syncs in real-time | Field Tech |  |
| iOS | Offline behaviour / graceful error | Dev / IT |  |
| iOS | Push notifications (if applicable) | Dev / IT |  |
| Android | APK install and sign-in | Dev / IT |  |
| Android | QR scan opens correct asset | Field Tech |  |
| Android | Android back-button navigation | Dev / IT |  |
| Data | Go Codes asset import matches source record count | Dev / IT |  |
| Data | Sticker scan resolves to correct GearOps record | Field Tech |  |
| Data | New gear allocation saves correctly | Office Mgr |  |

# 6. Asset Migration Plan

## 6.1 Migration Overview

The migration from Go Codes to GearOps has two components running in parallel: a data migration (digital) and a physical sticker replacement. Both must complete for each asset before it is considered fully migrated.

## 6.2 Pre-Migration Preparation

- Export a full CSV of all assets from Go Codes. Confirm row count.

- Back up Supabase production database (snapshot).

- Prepare the import script — test on staging with a 10-asset sample.

- Print all GearOps QR stickers (full batch + 10% spares for damage/errors).

- Prepare sticker application kit for field technicians (isopropyl wipes, sticker sheets, scanner device).

- Brief field technicians on the sticker replacement procedure.

## 6.3 Migration Checklist

Track every task below. Do not proceed to FULL rollout until PILOT tasks are complete and signed off.

|  | Task | Owner | Done? |
| --- | --- | --- | --- |
| PRE | Export all assets from Go Codes to CSV | Dev / IT | ☐ |
| PRE | Validate exported CSV row counts | Dev / IT | ☐ |
| PRE | Back up Supabase production database | Dev / IT | ☐ |
| PRE | Print new GearOps QR stickers (batch) | Project Lead | ☐ |
| PRE | Confirm pilot asset list (first 50) | Project Lead | ☐ |
| PILOT | Import pilot 50 assets into GearOps | Dev / IT | ☐ |
| PILOT | Remove old stickers from pilot assets | Field Tech | ☐ |
| PILOT | Apply new GearOps stickers to pilot assets | Field Tech | ☐ |
| PILOT | Scan each sticker – verify correct record loads | Field Tech | ☐ |
| PILOT | Confirm pilot sign-off before full rollout | Project Lead | ☐ |
| FULL | Import remaining assets (100–500) into GearOps | Dev / IT | ☐ |
| FULL | Remove old stickers from all remaining assets | Field Tech | ☐ |
| FULL | Apply new GearOps stickers to all remaining assets | Field Tech | ☐ |
| FULL | Allocate any new gear directly in GearOps | Office Mgr | ☐ |
| CLOSE | Decommission Go Codes system | Project Lead | ☐ |
| CLOSE | Archive Go Codes data (read-only backup) | Dev / IT | ☐ |
| CLOSE | Notify all staff Go Codes is retired | Project Lead | ☐ |

## 6.4 Sticker Replacement Procedure

For each asset in scope, field technicians should follow this exact sequence:

- Locate the asset and confirm its ID matches the migration batch list.

- Photograph the existing Go Codes sticker (for audit trail).

- Clean the surface with an isopropyl wipe and allow to dry.

- Remove the old Go Codes sticker.

- Apply the new GearOps QR sticker to the cleaned surface.

- Scan the new sticker with the GearOps app. Confirm the correct asset record opens.

- Mark the asset as complete in the migration tracking sheet.

Note: New gear acquired during or after the rollout must be entered directly in GearOps. Do not use Go Codes for any new assets from Phase 2 onwards.

# 7. Communication Plan

## 7.1 Stakeholder Notifications

| Audience | Message | Channel | Timing |
| --- | --- | --- | --- |
| Field Technicians | New app launching, training session details, sticker replacement schedule | Email + in-person briefing | 1 week before Phase 2 |
| Office / Admin Staff | Go Codes retirement date, GearOps web guide, who to contact for help | Email + training session | 1 week before Phase 4 |
| Dev / IT | Build schedule, deployment windows, on-call roster for go-live weekend | Slack / direct | Ongoing per phase |
| Management | Phase completion updates, any delays or risks escalated | Email summary | End of each phase |

## 7.2 Go-Live Announcement

Once Phase 4 is complete, send a go-live announcement to all staff including:

- GearOps is now live on Web, iOS (App Store), and Android (Google Play)

- Go Codes is now retired — do not use for any new entries

- Link to GearOps web app and App Store/Play Store listings

- Contact for questions or support

# 8. Risk Register

Review this register at each phase gate. Update likelihood and impact as the project progresses.

| Risk | Impact | Likelihood | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| Assets not fully catalogued in Go Codes | HIGH | MEDIUM | Audit all assets before migration begins. Reconcile discrepancies. | Project Lead |
| QR/barcode sticker placement errors | MEDIUM | HIGH | Print sticker batch test. Double-scan verification protocol after each application. | Field Tech |
| iOS App Store / TestFlight delays | MEDIUM | LOW | Submit early; allow 2-week Apple review buffer. Keep TestFlight as fallback. | Dev / IT |
| Supabase migration breaks production | HIGH | LOW | Run migrations on staging first. Use Supabase branching. Keep rollback script ready. | Dev / IT |
| Field staff resistance to new system | MEDIUM | MEDIUM | Hands-on training sessions. Cheat-sheet handout. Pilot with small group first. | Office Mgr |
| Data loss during Go Codes export | HIGH | LOW | Full CSV export + backup before migration. Validate row counts post-import. | Dev / IT |

# 9. Success Metrics

The following metrics define a successful deployment. Review these at the end of Phase 5.

| Metric | Target | Measurement Method |
| --- | --- | --- |
| Assets migrated | 100% of scoped assets | Migration checklist |
| Sticker scan accuracy | 100% correct record on first scan | Field verification log |
| iOS App Store live | App Store listing approved & public | App Store Connect |
| Android Play Store live | Play listing approved & public | Google Play Console |
| Go Codes decommissioned | Zero new entries post-cutover | Go Codes audit log |
| Zero P0 bugs at go-live | No critical issues in first 72 hrs | Bug tracker |
| Staff adoption rate | 80%+ using GearOps within 2 weeks | Login analytics (Supabase) |

# 10. Key Contacts

| Role | Name | Email | Notes |
| --- | --- | --- | --- |
| Project Lead | Shivam Verma | sverma@engsurveys.com.au | Primary decision maker |
| Dev / IT | TBC | TBC | Build & deploy lead |
| Field Tech Lead | TBC | TBC | Sticker rollout |
| Office Manager | TBC | TBC | Staff communications |

Document version: 1.0  |  Created: April 2026  |  Next review: Prior to Phase 2 gate